## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: 4 |  |  |  |  | Danny Belmonte | dbelmo2@uic.edu
Week Of: 4/4/2019 |  |  |  |  | Andrew Ciepiela | aciepi3@uic.edu
[5 empty] | John Almazan | jalmaz3@uic.edu
[5 empty] | Michael Lemus | mlemus6@uic.edu
|  |  |  | Team Number: 23 | Huihan Hu | hhu25@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
implemented the game where each game is one round and server sends a win/loss/draw message. | 1 | John Almazan
implemented the feature for the server to host multiple games and send messages to appropriate players. | 2 | John Almazan
implemented a simple way for a player to challenge another player, and for a player to accept a challenge. | 3 | John Almazan
implemented window that showed a list of clients that updates list whenever a client joins or leaves. | 4 | Danny Belmonte
implemenented disabling player buttons whenever a player is challenged to a game. | 5 | Danny Belmonte
implemented a way that once a player is in the game, the player challenging the player currently in the game will receive a message stating the player in unavailable | 6 | Michael Lemus
implemented a drop down menu of buttons for players to choose their opponent | 7 | Michael Lemus
implemented the return to lobby button once the game is completed / once the player player received the message that the player is already in a game | 8 | Michael Lemus
update the server GUI | 9 | Huihan Hu
update the client GUI | 10 | Huihan Hu